## ProjectSchedule
Project PoliDemoni | [8 empty] | ► Watch How to Make a Gantt Chart in Excel
[Company Name] |  |  | Project Start: | 2025-10-01
[Project Lead] |  |  | Today: | 2025-10-21
Total Estimated Cost: | 48700 |  | Display Week: | 1 |  |  |  | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17
 | time axis 2025-09-29 to 2025-11-23
TASK | ESTIMATED COST | ASSIGNED TO | PROGRESS | START | END | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30
Project Setup & Governance
Kickoff & scope confirmation | 1500 | Guerini |  | 2025-10-01 | 2025-10-02 |  | 2
Set governance, RACI & cadences | 1100 | Guerini |  | 2025-10-03 | 2025-10-07 |  | 5
Tooling setup (SharePoint/CRM) | 900 | Mutti |  | 2025-10-06 | 2025-10-10 |  | 5
Market & User Research (SMEs Bergamo)
Define ICP & buyer personas | 1300 | Zecchini |  | 2025-10-08 | 2025-10-14 |  | 7
Interview 8 SMEs & collect pains | 2200 | Zecchini |  | 2025-10-15 | 2025-10-29 |  | 15
Competitive scan & pricing ranges | 1400 | Bertasa |  | 2025-10-20 | 2025-10-31 |  | 12
Insights report & priorities | 1200 | Guerini |  | 2025-11-01 | 2025-11-05 |  | 5
Product Design (UX/UI)
Value prop & feature set (MVP) | 1600 | Guerini |  | 2025-11-06 | 2025-11-12 |  | 7
User flows & wireframes | 2400 | Mutti |  | 2025-11-10 | 2025-11-21 |  | 12
Clickable prototype | 2600 | Mutti |  | 2025-11-24 | 2025-12-05 |  | 12
Code Development (MVP)
Backend skeleton & database | 4200 | Bertasa |  | 2025-12-01 | 2025-12-19 |  | 19
Frontend components | 3800 | Mutti |  | 2025-12-08 | 2026-01-09 |  | 33
API integration & auth | 3600 | Bertasa |  | 2026-01-12 | 2026-02-07 |  | 27
QA & bug‑fix sprint | 2500 | Zecchini |  | 2026-02-09 | 2026-02-15 |  | 7
Cooperation & Partnerships
Map local partners (associations) | 900 | Zecchini |  | 2025-11-17 | 2025-11-24 |  | 8
Outreach & MoUs (3 partners) | 1400 | Guerini |  | 2025-11-25 | 2025-12-12 |  | 18
Partner onboarding kit | 800 | Guerini |  | 2025-12-15 | 2026-01-08 |  | 25
Marketing Prep & Assets
Messaging & sales deck | 1200 | Guerini |  | 2026-01-13 | 2026-01-20 |  | 8
Website landing & tracking | 1700 | Mutti |  | 2026-01-21 | 2026-02-03 |  | 14
Email templates & CRM sequences | 1100 | Zecchini |  | 2026-02-04 | 2026-02-14 |  | 11
Case study prototype | 900 | Bertasa |  | 2026-02-17 | 2026-03-03 |  | 15
Pilot with 3 SMEs
Select pilot clients & NDA | 700 | Guerini |  | 2026-03-02 | 2026-03-06 |  | 5
Deploy MVP & onboarding | 2100 | Mutti |  | 2026-03-09 | 2026-03-27 |  | 19
Collect feedback & iterate | 1500 | Bertasa |  | 2026-03-30 | 2026-04-10 |  | 12
Launch & Sales Enablement
Public launch (Bergamo) | 1000 | Guerini |  | 2026-04-16 | 2026-04-17 |  | 2
Outbound to 100 SMEs | 1800 | Zecchini |  | 2026-04-20 | 2026-05-08 |  | 19
Demos & proposals | 1600 | Guerini |  | 2026-05-05 | 2026-05-22 |  | 18
Wrap‑Up & Next‑Step Roadmap
Performance review & KPIs | 800 | Zecchini |  | 2026-05-25 | 2026-05-28 |  | 4
Roadmap v2 & budget | 900 | Guerini |  | 2026-05-29 | 2026-06-01 |  | 4
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2025 Vertex42 LLC
Note on I6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## AI
"IMPORTANT: Do not analyze, scan, or inspect any part of this workbook except the AI worksheet until you have fully read these instructions and acknowledged Strict Mode is ON."
AI Assistant
Instructions for the User
This worksheet provides guidance on using AI to help populate the template with a sample project schedule based on the information you provide below. Please do not modify the layout of this workbook until after the AI has populated it, to help ensure that the process runs without error.
Remember that AI has a tendency to make up false answers, so always verify results and modify as needed.
Step 1 | Answer the following questions in the space provided.
If you do not know the answer to a question, you can leave it blank.
Q: What is the name or title of your project?
Project PoliDemoni
Q: What are you trying to accomplish with this project?
we are trying to sell our product tu medium-small company
Q: When would you like the project to begin?
October 1st 2025
Q: When would you like the project to be completed by?
June 1st 2026
Q: In which city, state, country will this project be completed?
Bergamo, ITA
Q: What are the main steps or key parts of this project that you already know about?
Develop the Code part, Cooperating work, marketing, research for source
Q: How detailed would you like your project schedule to be?
detailed with big steps and with a good timeline
Q: Is there anything else I should know to help create your project schedule?
good design with good color spaces and headline
Q: If applicable, provide a list of names and their roles for assigning tasks.
Guerini, Zecchini, Mutti, Bertasa
Step 2A | Upload this file into a new chat with ChatGPT and copy the prompt below into the text box.
Copy this prompt ► | Please make me a copyable table of a project schedule, rendered with markdown format so it can be directly copied into an Excel file. After the header, use only one delimiter row (¦---¦---¦…¦). In the first column are the Tasks. Here you will place the phase titles and subtasks. The second column is the Estimated Cost. Here you will use the given project location to assume the correct currency, but enter only numeric values without currency symbols. The third column is called Assigned To. Here, you will use the list of names based on role, or include the general role title such as Project Manager, Inspector, Electrician, etc. Leave the fourth column, Progress, blank. The 5th column is the Start Date of the task, and the 6th column is the End Date. Every row that includes a phase title should have all other cells in that row empty. Always write empty cells as ¦ ¦ with two spaces. Based on the formatting described to you and the answers to the questions given, you will now generate the table. Come up with Phases, as many as needed, and subtasks for each phase. Tasks should be relevant and specific. Phase titles should be descriptive. Use general logic to assign team members, meaning generally only one task at a time per team member. Start and end dates should be realistic and based on educated guesses for how long that task should take. Rules for Editing the XLSX File Always use openpyxl when editing .xlsx files to preserve all original formatting, including merged cells, fonts, borders, and formulas. The end result of this conversation should be you giving the user a .xlsx file. Write all dates as real Excel date values (using Python datetime objects) and set only cell.number_format = 'yyyy-mm-dd' to apply the date format. Do not modify cell.style or other properties. You must follow all of the steps carefully and in order. Read and follow every word of every line. Do not skim or summarize. Here are a few questions the user may have answered to give you more information Q: What is the name or title of your project? Project PoliDemoni Q: What are you trying to accomplish with this project? we are trying to sell our product tu medium-small company Q: When would you like the project to begin? October 1st 2025 Q: When would you like the project to be completed by? June 1st 2026 Q: In which city, state, country will this project be completed? Bergamo, ITA Q: What are the main steps or key parts of this project that you already know about? Develop the Code part, Cooperating work, marketing, research for source Q: How detailed would you like your project schedule to be? detailed with big steps and with a good timeline Q: Is there anything else I should know to help create your project schedule? good design with good color spaces and headline Q: If applicable, provide a list of names and their roles for assigning tasks. Guerini, Zecchini, Mutti, Bertasa Do not wrap the table in backticks. Always write empty cells as ¦ ¦ with two spaces. Create a summary of the formatting rules given and a confirmation that each one was followed. Fill in the background of each row in a phase with a color specific to that phase, using light colors that will work well with the black text. Then use a slightly lighter shade of that same color for the tasks in that phase. Now take that table and copy it into B7 of the ProjectSchedule worksheet within the file, but don't include the table header when you paste it in because I already have the table header in row 6. Edit B1 to be the project title and F2 to be the project start date, all in the ProjectSchedule worksheet.
Step 2B | If you do not have the paid version of ChatGPT, copy the prompt below instead. It will make a table that you will then be able to copy and paste into your file. To keep the formatting of the template, use Ctrl+Shift+V to paste.
Copy this prompt ► | Please make me a copyable table of a project schedule, rendered with markdown format so it can be directly copied into an Excel file. After the header, use only one delimiter row (¦---¦---¦…¦). In the first column are the Tasks. Here you will place the phase titles and subtasks. The second column is the Estimated Cost. Here you will use the given project location to assume the correct currency, but enter only numeric values without currency symbols. The third column is called Assigned To. Here, you will use the list of names based on role, or include the general role title such as Project Manager, Inspector, Electrician, etc. Leave the fourth column, Progress, blank. The 5th column is the Start Date of the task, and the 6th column is the End Date. Every row that includes a phase title should have all other cells in that row empty. Always write empty cells as ¦ ¦ with two spaces. Based on the formatting described to you and the answers to the questions given, you will now generate the table. Come up with Phases, as many as needed, and subtasks for each phase. Tasks should be relevant and specific. Phase titles should be descriptive. Use general logic to assign team members, meaning generally only one task at a time per team member. Start and end dates should be realistic and based on educated guesses for how long that task should take. Here are a few questions the user may have answered to give you more information Q: What is the name or title of your project? Project PoliDemoni Q: What are you trying to accomplish with this project? we are trying to sell our product tu medium-small company Q: When would you like the project to begin? October 1st 2025 Q: When would you like the project to be completed by? June 1st 2026 Q: In which city, state, country will this project be completed? Bergamo, ITA Q: What are the main steps or key parts of this project that you already know about? Develop the Code part, Cooperating work, marketing, research for source Q: How detailed would you like your project schedule to be? detailed with big steps and with a good timeline Q: Is there anything else I should know to help create your project schedule? good design with good color spaces and headline Q: If applicable, provide a list of names and their roles for assigning tasks. Guerini, Zecchini, Mutti, Bertasa Do not wrap the table in backticks. Always write empty cells as ¦ ¦ with two spaces. Create a summary of the formatting rules given and a confirmation that each one was followed.
Instructions for AI (Do Not Edit)
Prompt Instructions
Please make me a copyable table of a project schedule, rendered with markdown format so it can be directly copied into an Excel file. After the header, use only one delimiter row (¦---¦---¦…¦). In the first column are the Tasks. Here you will place the phase titles and subtasks. The second column is the Estimated Cost. Here you will use the given project location to assume the correct currency, but enter only numeric values without currency symbols. The third column is called Assigned To. Here, you will use the list of names based on role, or include the general role title such as Project Manager, Inspector, Electrician, etc. Leave the fourth column, Progress, blank. The 5th column is the Start Date of the task, and the 6th column is the End Date. Every row that includes a phase title should have all other cells in that row empty. Always write empty cells as ¦ ¦ with two spaces. Based on the formatting described to you and the answers to the questions given, you will now generate the table. Come up with Phases, as many as needed, and subtasks for each phase. Tasks should be relevant and specific. Phase titles should be descriptive. Use general logic to assign team members, meaning generally only one task at a time per team member. Start and end dates should be realistic and based on educated guesses for how long that task should take.
Additional Instructions
Do not wrap the table in backticks. Always write empty cells as ¦ ¦ with two spaces. Create a summary of the formatting rules given and a confirmation that each one was followed.
Fill in the background of each row in a phase with a color specific to that phase, using light colors that will work well with the black text. Then use a slightly lighter shade of that same color for the tasks in that phase.
Now take that table and copy it into B7 of the ProjectSchedule worksheet within the file, but don't include the table header when you paste it in because I already have the table header in row 6. Edit B1 to be the project title and F2 to be the project start date, all in the ProjectSchedule worksheet.
Rules for Editing the XLSX File
Always use openpyxl when editing .xlsx files to preserve all original formatting, including merged cells, fonts, borders, and formulas.
The end result of this conversation should be you giving the user a .xlsx file.
Write all dates as real Excel date values (using Python datetime objects) and set only cell.number_format = 'yyyy-mm-dd' to apply the date format. Do not modify cell.style or other properties.
You must follow all of the steps carefully and in order.
Read and follow every word of every line.
Do not skim or summarize.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2025 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 400 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.